## Slide 1
WP5: Innovation Ecosystem
Folkwin Poelman (WP5 lead), with a lot of contributions of the WP5 team members
This project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No. 842009

## Slide 2: WP5 Current status

## Slide 3: WP5 current status C&D
Deliverable D5.2 Stakeholder Exchange Platform Report (M12) was submitted in October 2020.
NIVA website has been improved, and new content is being added on an ongoing basis.
WP5 workplan has been updated, reflecting the new reality of pandemic situation and adapting communication and dissemination activities accordingly.
Notes: Due to the postponement/cancellation of the Stakeholder Forum in Dublin, this deliverable was not delivered in May 2020. WP5 organized 3 webinars (in June and July 2020) instead of Stakeholder Forum and an overview (including presentations) of these webinars was given in this deliverable.

## Slide 4: WP5 current status C&D
The NIVA newsletter is ready to distributed
New webinars are planned for December:
  3rd Dec: FAST and FMIS/field book
  10th Dec: Green Deal and carbon farming
  17th Dec: Capigi and digital rights
Discussion has been started on how to best communicate the results of work done in use cases (developed tools).

## Slide 5: WP5 D5.7 Practice Abstracts 1st round

## Slide 6: Practice Abstracts – what and why
EIP-AGRI1 common format
  Communicating about projects and results through the use of a common format, via EIP-AGRI database for multi-actor projects
  General information about the project and project partners
  Includes one or more „Practice Abstract(s)“
Practice Abstracts
  Help to communicate results of the project in a concise and easy understandable way to practitioners (farmers, researchers etc)
  Good opportunity to disseminate information about the NIVA, the work done in all Use Cases and how the results of this work can be implemented into practice
  In English + local language

## Slide 7: NIVA D5.7 and D5.8
Practice Abstracts to be submitted twice
  D5.7 Practice Abstracts – 1st Round → M18
  D5.8 Practice Abstracts – 2nd Round → M36
  According to Grant Agreement 13 Practice Abstracts at least, 5 to be submitted as part of D5.7, additional 8 as part of D5.8
Current status
  D5.7 submitted in Nov 2020, including 8 Practice Abstracts
  Contributions expected for the next round, each Use Case can submit several ones
  Whom to contact → WP5: Folkwin (folkwin.poelman@rvo.nl), Peter (peter.paree@zlto.nl), Jane (jane.jager@pria.ee)

## Slide 8: EIP-AGRI common format – information about project partners
Contact details of each project partner expected, which will be published if they consent
D5.7 → contact details filled in according to WP2 contact list, publication consent ticked only for project coordinator
D5.8 → publication consent for all partners? Please inform about your consent
  Sander sander.janssen@wur.nl
  WP5

## Slide 9: WP5 C&D templates

## Slide 10: WP5 C&D templates
WP5 created several templates for C&D purposes: https://wageningenur4.sharepoint.com/:f:/r/sites/NIVA/Gedeelde%20documenten/NIVA_forPartners/Workpackage%20folders/WP5/Tasks/T5.6%20Dissemination%20and%20Communication/Templates?csf=1&web=1&e=WyPdPO
Presentation, letter heads, banners, deliverable reports, and many more
Please always check the link on Sharepoint for the most recent versions!

## Slide 11: WP5 next steps

## Slide 12: WP5 next steps
The upset of an Innovation Ecosystem and stakeholder engagement are important elements of the NIVA project.
Tuesday 24 November WP5 organises a workshop:
The main topic of this interactive workshop is to make an inventory of the needs of the NIVA partners, but also of the stakeholders. We are now in the middle of the NIVA project. The question is how we succeed to prolong the work of NIVA after the project will end in May 2022.
During the workshop we will use Miro boards: https://miro.com/app/board/o9J_lf4vYPM=/
Please register in time (before the workshop!!)

## Slide 13: THANK YOU!
This project has received funding from the european union’s horizon 2020 research and innovation programme under grant agreement no. 842009